## Slide 2: Supplement for Chapter 3 Project Management

## Slide 3: Learning Objectives
Calculate the probability of a project being completed on time.
Calculate the cost of “crashing” a project and the amount of time a project can be accelerated.
Calculate the earned value of an ongoing project to assess its current status throughout development.

## Slide 4: Operations Profile: Fast Tracking Manchester’s New Airport Development
In 2015, Manchester Airport announced plans for a $1.5 billion renovation to expand the size.
Building or renovating airports is a massive project undertaking, with numerous stakeholders and often, billions of dollars at risk.
Having a clear sense of the project’s goals, the means to minimize disruptions for current travelers, and make the process as risk-free as possible are the keys to a successful project that will benefit the citizens of Manchester and air travelers for decades to come.

## Slide 5: Determining the Probability of a Project Being Completed on Time
Sometimes it is extremely difficult to accurately estimate the durations of a project’s activities.
In these situations such PERT estimates are helpful.
Expected duration of an activity:
TE = (a + 4m + b)/6
TE = estimated time for activity
A = most optimistic time to complete the activity
M = most likely time to complete the activity
B = most pessimistic time to complete the activity

## Slide 6: Project Eagle
Market research project to be undertaken by a small firm in Columbus, Ohio.

## Slide 7: Network Diagram for Project Eagle

## Slide 8: Expected Time and Variance for Project Eagle
The variance of the duration of an activity is s2 = [1/6(b – a)]2
where b is the most pessimistic time and a is the most optimistic.

## Slide 9: Completed Activity Network for Project Eagle

## Slide 10: The Probability Distribution for Project Eagle’s Completion Times
σp2 = project variance = Σ (variances of activities on the critical path)
Proj. variance = 1.78 + 1.00 + 4.00 + .69 + .25 = 7.72
Project standard’s deviation (σp) is:
√Project variance = √7.72 = 2.78 weeks

## Slide 11: Calculating Probability of Finishing on Time
Z = (due date – expected date of completion)/ σp
= (32 – 30)/2.78 or 0.72
Using a normal distribution table, Z value of 0.72 indicates a probability of 0.7642.
There is a 76.42% chance that Project Eagle will finish on or before the critical date of 32 weeks.

## Slide 12: Calculating the Time−Cost Trade-Offs of Crashing a Project

## Slide 13: Calculating the Time−Cost Trade-Offs of Crashing a Project (Cont’d.)
We can calculate various time–cost trade-off combinations for a project’s crash options by determining the slope for each activity using the following formula:

## Slide 14: Example 3S.1: Choosing the Activities to Crash
Notes: Suppose we have a project with the eight activities listed Table 3S.3.
The table also shows the normal durations and costs and crashed durations and costs of the activities. (Assume that the costs listed include both the fixed and variable costs for each activity.)
Which activities should we crash and for how many days each?

## Slide 15: The Costs of Crashing Each Activity
Notes: We can then use the formula to calculate the costs per unit of crashing each activity.

## Slide 16: The Fully Crashed Activity Network for the Project
Notes: We determined that the initial cost of the project using normal activity durations is $22,450.
The network also shows that the project’s critical path is A D E H, or 19 days.

## Slide 17: The Cost of the Project Versus the Days Saved
Notes: Crashing Activity A is the least expensive. Crashing Activity A by 1 day will increase the project’s costs from $22,450 to $22,700.
Fully crashing Activity A will shorten the project’s duration to 25 days, while increasing the project’s costs to $22,950, as Table 3S.5 shows
Activities B and G are the next candidates for crashing at $300 per day each.
Neither of these two activities is on the project’s critical path, however, so the overall benefit of shortening them may be minimal. Activity D cannot be shortened.
The cost per unit to crash E is $1,750, and the cost per unit to crash H is $2,000. Crashing Activity E by 1 day will increase the project budget from $22,950 to $24,700. Fully crashing it by 3 days (shortening it from 9 days to 6), increases the budget to $28,200.
Since Activity H costs $2,000 per day to crash fully crashing it by three days (shortening it from 8 days to 5) will add another $6,000 to the budget.

## Slide 18: Graphic Representation of The Cost of the Project Versus the Days Saved
Notes: Note that the critical path is unchanged. The trade-off between the costs and the project’s duration is graphed in Figure 3S.6.
As each project activity has been crashed in order, the overall project budget increases. However, Figure 3S.6 also demonstrates that after crashing activities A, E, and H, there is little to be gained by crashing any of the other activities.
The overall length of the project cannot shrink below 19 days, and the additional crashing merely adds costs to the budget. Therefore, the optimal crash strategy for this project is to crash only activities A, E, and H for a total cost of $11,750 and a revised project cost of $34,200.

## Slide 19: Calculating a Project’s Earned Value
Terminology for the EVM Method
PV: Planned value. A cost estimate of the budgeted resources scheduled across the project’s life cycle.
EV: Earned value. The real budgeted cost, or “value,” of the work actually performed to date.
AC: Actual cost of the work performed.
SPI: Schedule Performance Index. SPI=EV/PV
CPI: Cost Performance Index. CPI=EV/AC
BAC: Budgeted cost at completion. The total budget for a project at its completion.

## Slide 20: Creating Project Baselines
Establishing the project’s baseline requires just two pieces of data: the work breakdown structure and a time-phased budget for the project.
The work breakdown structure identified the individual work packages and tasks necessary to accomplish the project.
The time-phased budget allows us to identify the correct sequencing of tasks, and it enables the project team to determine the points in the project when budgeted money is likely to be spent as those tasks are completed.

## Slide 21: EVM Method in the Project Tracy Example
Notes: Assume that it is now week 30 of the project and that we are attempting to assess the project’s status.
Also assume that there is no difference between the projected project costs and actual expenditures; that is, the project’s budget is being spent within the correct time frame.
However, suppose we were to discover that installation was only half-completed, and project testing had not yet begun.
Consider the revised data for Project Tracy listed in Table 3S.6.

## Slide 22: EVM Method in the Project Tracy Example
Notes: Calculating the earned value of these work packages is fairly simple.
As Table 3S.7 shows, we can modify the previous table to focus exclusively on the information we need to determine the earned value.
We do so by multiplying the percentage of each work package completed by its planned value (budgeted cost) in order to determine the earned value to date for the package as well as the overall project.
In this case, the project’s earned value at the 30-week point is $51,000.

## Slide 23: Steps in the Earned Value Management Method
Clearly define each activity in the project
Create the activity and resource usage schedules.
Establish a time-phased budget.
Total the actual costs each activity to arrive at the actual cost of the work performed (AC).
Compute the value of the work done on each task by multiplying the percentage of it completed by its planned value (budgeted cost).
Calculate both a project’s budget variance and schedule variance while it is still in process.

## Slide 24: Earned Value Table for Project Janus
Notes: The project began in January. We are interested in calculating its earned value as of the end of June.
Each month, we can then plot the actual expenses for each activity.
These sets of figures are added to the bottom four rows of the table.
This information alone won’t helps us truly determine of the status of the project.
To do that, we also need to how much of the project was completed by the end of March---not just the amounts budgeted and spent on the project.

## Slide 25: Schedule Variances for Project Tracy
Notes: The first value we require is the planned value (PV). This value can be found as the cumulative planned costs at the end of the month of June ($103,000).
We have also calculated that the earned value (EV) at the end of the month of June totals $44,000.
The schedule variances that are of interest to us are the Schedule Performance Index (SPI) and the estimated time to completion.
The SPI is determined by dividing the EV by the PV. Table 3S.9 shows this calculation ($44,000/103,000 = .43).
Because the SPI is telling us that we are only operating at 43% efficiency in implementing the project, we take the reciprocal of the SPI times the original project schedule to determine the projected actual timeframe for the project’s completion (1/.43 x 7 = 16.3 months). This is bad news. Recall that the project was only supposed to last 7 months. At this pace it will take a total of 16.3 months to complete.

## Slide 26: Cost Variances for Project Tracy
Notes: Although we are running over 10 months late, can we make similar projections about how much the project will finally cost? The answer is yes.
We can do so as long as we have two very important pieces of data—the actual cost (AC) of the work performed to date and the earned value (EV) to date.
The earned value has already been calculated ($44,000), and now we turn back to Table 3S.8 to locate AC. The cumulative actual cost at the end of June was $78,000.
We calculate cost variance by dividing the EV by AC, or $44,000/78,000 = .56.
That is the cost performance index (CPI) for this project.
Determining the projected cost of the project involves taking the reciprocal of the CPI multiplied by the project’s original budget ($118,000).
The bad news is that this project is not only far behind schedule, it is also projected to cost over $210,000, a significant cost overrun.

## Slide 27: The Earned Value and Project-Status Slippage
Notes: Finally, as Figure 3S.7 illustrates, we can plot these variances on a graph that shows the difference between the EV (earned value) and PV and AC.
This example underscores how misleading simple S-curves can sometimes be.
For example, in this case we discovered that at the end of June, the difference between the AC ($78,000) and PV ($103,000) was $25,000.
Although the analysis at that point showed that we had underspent our budget slightly, the status of the project in terms of its earned value shows that it is in trouble. This example demonstrates the advantages of using the earned value method to get a more accurate assessment of projects.