## Slide 2: Chapter 3: Project Management

## Slide 3: Learning Objectives
Describe the importance of projects to a firm, identify the people and teams that work on projects, and list the qualities that make a project a success.
Identify the stages of the typical life cycle of a project.
Explain how scope management techniques, statement-of-work documents, work breakdown structures, and risk management principles enable firms to conceptualize, plan, and organize projects
Use analytical tools to calculate project schedules.

## Slide 4: Learning Objectives (Cont’d)
Identify the main supply chain activities of a project and the qualities that should be considered when designing the project’s supply chain.
Demonstrate how to execute, track, and terminate projects.
Identify the critical steps in planning for sustainability in projects.
Discuss issues related to global project management.

## Slide 5: Operations Profile: Nissan LEAF Project Bugs
©iStockphoto.com/joel-t

## Slide 6: Projects: Importance, Teams, and Success
A project is a unique venture with a beginning and end, conducted by people to meet established goals within certain cost, schedule, and quality parameters.
  The Hoover Dam
  Space Station Freedom
  Apple’s creation of the new iPad.
  Bechtel’s construction of a large-scale chemical refining plant in South Africa.
  The West Coast High-Speed Route Modernization

## Slide 7: Project Management and Project Characteristics
Project management is the application of knowledge, skills, tools, and techniques to project activities to meet the project requirements.
All projects share the following characteristics:
  They are complex and unique
  They have a clear goal or set of goals
  They are limited by their budgets, schedules, and resources
  They are customer focused
  Shortened Product Life cycles
  Narrow Product-Launch Windows
  Increasingly complex and technical products and services

## Slide 8: Why Projects?
Reasons that companies use projects to achieve their strategic goals.
Shortened Product Life cycles.
Narrow Product-Launch Windows
Increasingly complex and technical products and services.
The emergence and integration of global markets.

## Slide 9: Project Teams
Project managers have a huge impact on a project’s success or failure.
Project leaders act as mini-CEOs for their projects.
A challenge that project managers face is that the team members working on the project typically are loyal to their functional departments rather than to the project team itself.
Sometimes the team members are employees of other organizations that a firm is partnering with.

## Slide 10: How Project Teams Are Structured

## Slide 11: How Project Teams Are Structured

## Slide 12: What Makes a Project Successful?
A project’s success must be evaluated by the elements that characterize the project.
  Time: Projects have a definite beginning and end.
  Cost: Projects are constrained by their budgets.
  Quality: All projects should be developed with a set of specifications that clearly state what the project is.
  Client satisfaction: The client for any project is the party (either internal or external to the organization) for whom the project is intended.

## Slide 13: Operations Profile – The Expeditionary Fighting Vehicle
Scott J. Ferrell/CQ-Roll Call Group/Getty Images

## Slide 14: Conceptualizing Projects
The development of a problem, or need, statement
An analysis of alternatives
Information gathering
Clearly stated objectives for the project
Statement of work (SOW):
  The introduction and background discussion
  The technical description of the project
  The timeline and milestones
Notes: The statement of work is a detailed description of the work required for the project. The document summarizes the work done during the conceptualization phase. Thus, it can help a project team stay on track in terms of what it is supposed to ultimately deliver. An effective SOW contains details about the project, a technical description of the project, and a timetable for completion.

## Slide 15: Planning
Work Breakdown Structures (WBS)
The WBS is a process of breaking down a project’s overall mission into step-by-step tasks.
Under each of the deliverables are additional activities, usually referred to as work packages.
Notes: Note that it is also relatively easy to create a WBS using Microsoft (MS) Project, as Screenshot 3.1 demonstrates.
Screenshot 3.1 shows a partial WBS for the wedding reception project created using the MS Project WBS option, which can distinguish between Project Level headings, Deliverable headings, and Work Package headings.

## Slide 16: Employing Risk Management Techniques
Risk management is the process of anticipating and figuring out how to respond to a project’s risks prior to beginning the project.
The risk management process involves three steps:
  1) identifying risks
  2) analyzing the probability of risks occurring and their consequences
  3) formulating risk mitigation strategies.
Notes: Share the risk. When multiple organizations develop a project, they often share the risks proportionally.
Transfer the risk. In some circumstances, it may be possible to use a contract to effectively transfer the risk to another party.
Document the risk. Another way to deal with risks is to thoroughly document them as part of the project’s development.

## Slide 17: Scheduling Projects
Project scheduling is the process of converting a project’s goals into a logical method for completing them on time.
Deterministic estimation is associated with the critical path method (CPM).
Probabilistic estimation is associated with the Program Evaluation and Review Technique (PERT).

## Slide 18: Program Evaluation and Review Technique (PERT)
The optimistic time (a) – the time an activity will take if everything happens as planned.
Most likely time (m) – the most realistic time to complete the activity.
Pessimistic time (b) – the time an activity will take if nothing happens as planned.
s2 = [1/6 (b – a)]2
TE = (a + 4m + b)/6

## Slide 19: PERT Example
Suppose we wished to determine the expected times (TE) for a series of activities a through e

## Slide 20: Precedence Diagrams and Gantt Charts
Precedence diagramming is the process of creating a chart that shows a project’s activities and indicates how they should logically be coordinated with one another.
Gantt chart links project activities to a schedule, which is usually a calendar.
Notes: We can also construct the Gantt chart using MS Project.
The advantage of using a software package such as MS Project is that it automatically syncs the activities to a calendar and provides expected start and finish dates.

## Slide 21: Creating Network Diagrams
Network diagramming is a logical, sequential process that requires the project manager to consider the order in which activities should occur to schedule projects as efficiently as possible.
Activity on node (AON) network method, uses the node to represent the individual project activity and the path arrows represent the sequencing of tasks.
The activity on arrow (AOA) method uses arrows to represent the activities.

## Slide 22: Creating Network Diagrams

## Slide 23: Labeling Nodes
Early Start (ES): This is the earliest possible date on which an activity can start.
Early Finish (EF): Early finish is defined as: ES + activity duration = EF.
Late Start (LS): This is the latest possible date that an activity may begin without delaying the project.
Late Finish (LF): LS + activity duration = LF.
Activity Slack: Slack= LS – ES (or LF – EF).

## Slide 24: Constructing the Critical Path
Site preparation example and the information in Table 3.2.
Notes: Path 1: A – B – F – H – J = 4 + 4 + 4 + 2 + 4 = 18 days
Path 2: A – C – E – H – J = 4 + 2 + 2 + 2 + 4 = 14 days
Path 3: A – C – E – G – J = 4 + 2 + 2 + 2 + 4 = 14 days
Path 4: A – D – I – J = 4 + 5 + 3 + 4 = 16 days
Because path 1 is the longest, it is the critical path for our project, which is expected to take 18 days to complete. Activities A, B, F, H, and J are the critical activities.

## Slide 25: Forward Pass Calculations
Add all activity times (ES + Dur = EF) along each path as we move through the network.
Carry the early finish (EF) time to the activity nodes immediately succeeding the recently completed node.
At a merge point, the largest preceding EF becomes the ES for that node.

## Slide 26: Backward Pass Calculations
Subtract the activity times (LF – Dur = LS) along each path as we move through the network.
Carry back the late start (LS) time to the activity nodes immediately preceding the successor node.
In the case of a burst point, the smallest succeeding LS becomes the LF for that node.
Notes: Once we have completed the backward pass, we can determine the slack time, or float, for each activity as well as for each path through the network.
Recall that the slack tells us the amount of time an activity can be delayed without delaying the overall project.
The slack time, which is shown in italics in the node, is found by using one of two equations: LF – EF = Slack or LS – ES = Slack.

## Slide 27: Crashing the Project
Crashing is the process of speeding up a project’s remaining activities in order to move its completion date forward.
Part of a crashing a project includes calculating the dollar-per-day trade-off, i.e., how much money must be spent to save one day in the project’s schedule.

## Slide 28: Supply Chain for Projects
Supply Chain Activities for Projects
  Procurement
  Fabrication
  Distribution
Designing a Project’s Supply Chain
  Setting Goals for the Supply Chain
  Doing an Environmental Analysis
  Coordinating and Planning
  Controlling
Notes: Once the supply chain is set up, it needs to be scrutinized continuously to ensure it is the most efficient, reliable, and highest-quality chain attainable.

## Slide 29: The S-Curve and Earned Value Management
The earned value management (EVM) method calculates the value generated by the project as well as the budgeted and actual costs at a certain point time.
Notes: At the end of each period (week, month, or quarter), we simply total the project’s expenditures to date and compare them to the budget.
Any significant deviations between them reveal a potential problem.
The S-curve also provides real-time tracking information because expenditures can be continually updated and the new values plotted on the graph.

## Slide 30: Terminating the Project
A tremendous amount of paperwork must be archived during this stage, including schedule and planning documents, etc.
The success of a lessons learned process is highly dependent upon senior managers enforcing the archiving of critical historical information.
The lessons learned serve as a valuable form of organizational learning
Novice project managers can access and learn from information provided by other project managers reporting on past projects.

## Slide 31: Lessons Learned: Fossil Fuels Unpopularity Leading to Project Cancellations
A combination of social pressures, concern for the environment, and lower prices due to a recent glut of oil on the international market have led to the cancellation or postponement of a number of expensive projects in the U.S.
Notes: The popularity of energy projects have been shown to be heavily dependent on broader federal and state energy policies.
Economic conditions also affect the willingness to fund and support these projects
Ultimately, one of the challenges with gaining wide acceptance of an energy project is winning the “hearts and minds” of the wider population who are affected by the results of the project.
With fossil fuel projects, the debate often centers on “jobs vs. the environment” arguments that can lead to difficult tradeoffs and passionate debate.

## Slide 32: Sustainability Issues in Project Management
Critical steps in planning for sustainability in projects:
Setting sustainability expectations.
Identify opportunities to reduce costs.
Using sustainability risk management.
Emphasize value maximization.
Identify specific sustainability requirements that are to be pursued.
Engage suppliers and subcontractors in sustainable ways.
Motivate the project team.
Notes: Project management offers a number of ways in which sustainable operations may be realized, both through the commitment of organizations to use their project activities in support of sustainable goals and initiatives, as well as through allowing sustainability to become part of a firm’s project management practices.

## Slide 33: Globalization in Projects
Globalization implications for projects:
The need to develop global project management standards.
The increased use of geographically-dispersed teams.
The use of virtual technologies.
Notes: As multinationals are able to make use of the expertise of their employees around the globe, the types of projects they will pursue will increasingly call for expertise in virtual settings, working with members of multiple cultures, and the joint challenges of building trust and establishing the best modes for communicating across national borders and multiple time zones.